## Аркуш1
1) Define classes to parse and train | - | 1 week to 22 of April | Defined the problem as binary classification of people with and without masks
2) Create initial parser, code review, optionally gather some photos | Put code to git | 1 week to 29 of April | Pexels,Google,Usplash,Pixabay,Instagram
3) Implement duplicates cleaning (with hash or smth else, search for related libraries). | - | 2 weeks to 07 of May | Done
4) Clean trash from dataset using NN (logistic regression/VGG) | - | 2 weeks to 07 of May | Used VGG
5) Check duplicates cleaning, provide precise function, search for libraries | - | 2 weeks to 07 of May | Done
6) Play around with a model, try to gather test dataset and evaluate it on it. | - | 2 weeks to 07 of May | Done
7) Start writing telegram bot , research | - | 3 weeks to 14 of May | Done
8) Write telegram bot, test it (maybe set up python server with sockets/tornado/ or using tensorflow service) | - | 3 weeks to 14 of May | used tensorflow-serving
9) Gather everything togather, run the bot, test it | - | 3 weeks to 14 of May | Done
10) Working on models prediction improvement | - | 4 weeks to 21 of May | Created additional class, gathered additional dataset
11) Provide feedback about project, create presentation | - | 5 weeks to 28 of May | Done